## Index
Project Management Document Video Series
Document Name
Assumption Log
Issue Log
Change Log
Risk Register
Stakeholder Reister
RTM
RACI
. |  |  |  | RAM
OBS
Project Kick-off meeting checklist
Retrospective (Lesson Learned)
0
| This is useful if you are |  | I call it as LLD
|  | A project manager or PMO | More than 50% pages of PMI-PMBOK book
|  | Preparing for PMP cerfification exam | Continuoous Improvement
|  | Preparing for PRINCE2 certification exam | In Agile, it is retrospective.
|  | ISOBEX Certified Manager certification exam | Retrospective in Non IT companies
in both projects and operations

## Assumption Log
|  | Templete Developed By - ISOBEX |  | www.isobex.com
Assumption Log
Project Name | Construction of Cotton Mill | Location | Pune, India | Version No. | 1
Project Manager | John Smith | Client Name | Cotton Co-operative Society | Updated On | 27/02/2020
Start date | 2020-01-01 | End date | 2020-07-01
Assumption No. | Assumption Description | Assumption Category (Budget/Product/Procurement) | Impact rating (high/medium/low | Date identified | Validation assigned to | Validation due date | Status (open/Close) | Comments
1 | Additional funding will be available for procurement of high cost equipments to complete the project on time | Procurement | high | 24/02/2020 | John Smith | 2020-03-03 | Open | 24/02/2020: Highlighted to management. 27/02/2020: Paul started working on it

## Issue Log
|  | Templete Developed By - ISOBEX |  | www.isobex.com
Issue Log
Project Name | Construction of Cotton Mill | Location | Pune, India | Version No. | 1
Project Manager | John Smith | Client Name | Cotton Co-operative Society | Updated On | 27/02/2020
Start date | 2020-01-01 | End date | 2020-07-01
Issue No. | Status (New/Open/WIP/Closed) | Issue category | Description | Date identified | Priority (High/Medium/Low) | Owner/assigned to | Estimated turnaround (ETA) Date | Impact | Comments
1 | Open | Resource | Availability is not matching resource plan | 12-Aor-2020 | High | John Smith | 2020-04-20 | Impacting project execution, xpecifically product development phase | 13-Apr: Assigned to John 14-Apr: John has highlighted to resource manager 15-Apr:

## Change Log
|  | Templete Developed By - ISOBEX |  | www.isobex.com
Change Log
Project Name | Construction of Cotton Mill | Location | Pune, India | Version No. | 1
Project Manager | John Smith | Client Name | Cotton Co-operative Society | Updated On | 27/02/2020
Start date | 2020-01-01 | End date | 2020-07-01
Change No. | What is the change? | Is addition or change in existing work package? | Impacted work packages | Impacted functionality | Date identified | Priority (High/Medium/Low) | Efforts required to implement the change | Additional cost required | Change Owner | Is reviewed by change control board? | Status (Approved/Rejected/Defered/New) | Comments
1 | An additonal step is required to approve changes related to cost more than 10000 USD. | Addition | WBS 1.2.1, WBS 1.3.4 | Current approval work flow in system Eunction trigerring email notification for status of approvals | 2020-03-21 | High | 80 hrs | 4000 USD | Grifith Johnson | NO | New | 21-Mar: Change is registered in change log. Pending for review by CCB.

## Risk Register
|  | Templete Developed By - ISOBEX |  | www.isobex.com
Risk Register
Project Name | Construction of Cotton Mill | Location | Pune, India | Version No. | 1
Project Manager | John Smith | Client Name | Cotton Co-operative Society | Updated On | 2020-05-09
Start date | 2020-01-01 | End date | 2020-07-01
Risk Id | Date Identified | Risk Description | Response Strategy (Accept/Avoid/Transfer/Mitigate etc. | Risk Owner | Probability of Occurance (High/Medium/Low | Impact (High/Medium/Low) | Risk Exposure (P*I) | Contingency plan | Impacted work packages/Area/Functionality | Status (Open/Close | Target Closure Date | Risk Ageing (days) | Comments
PRJ123-01 | 2020-05-05 | As per the domain experts, estimations provided by vendor is inaccurate. With this estimation, we may get poor quality of the deliverables. | Mitigate - Ask vendor to revise the estimate | sailly | High | High |  | Keep some strong quality processes to ensure high quality of deliverables | revenue calculation module and all work package | Open | 2020-05-15 | 5 | 5-May: Risk highlighted with conern department 7-May: Call has been setup vendor to understand the estimate. 9-May: Asked vendor to revise the estimates

## Stakeholder Register
|  | Templete Developed By - ISOBEX |  | www.isobex.com
Stakeholder Register
Project Name | Construction of Cotton Mill | Location | Pune, India | Version No. | 1
Project Manager | John Smith | Client Name | Cotton Co-operative Society | Updated On | 2020-05-09
Start date | 2020-01-01 | End date | 2020-07-01
No. | Name | Title | Contact information | Major expectation | Role & Responsibility | Power(High/Medium/Low) | Interest (High/Medium/Low | Power-Interest Grid quadrant | Remarks
1 | Jonathan M | Program Manager | Hartland Road, Troy Cell - +123453463 jonathan@c-org.com | 1. None of the vendor should compromise on quality. 2. Need quality report on every Friday. | Jonathan is first point of contact for any queries about testing and quality. | High | High | Actively Engage

## RTM
RTM for Public Library Renewation Project
| Reading Area |  |  |  | Book Storage |  |  | Public Meeting Space |  |  | Children's Area |  | Audio |  |  | Office Space |  | Computers
| Magazines | Newspapers | Comfortable chair-25 | Patron Desk -2 | 150000 books | 15 different categories | Sinage for easy locating | Rooms | Separate entrance | Drop down screen | Small chairs 80% | Story time locale | Room for audio books and musics | Shalves for audio book -15 | Racks for music-15 | Offices - 4 | Cubes - 15 | For public use-50 | For visitors service desk - 12 | For staff - 20 | With audio capability - 5 | Printers
Objective
Improve access to job resource by 20%
Improve children's reading section
Provide a pleasant place for community members to meet
Replace the existing library by end of next quarter

## RACI
|  | Templete Developed By - ISOBEX |  | www.isobex.com
RACI
Project Name | Construction of Cotton Mill | Location | Pune, India | Version No. | 1
Project Manager | John Smith | Client Name | Cotton Co-operative Society | Updated On | 2020-05-09
Start date | 2020-01-01 | End date | 2020-07-01
| Rakesh (PM) | John(Lead) | Julie (Team Member) | Ibrahim (lead) | Julian | Amar(Quality Manager)
Preparing design | A,R |  | R | C | C | I
Review of design | A | R | C |  |  | I
Reporting status of the work |  |  | C | C | R | A
Quality Inspection | C | C,I |  | R |  | A
A=Accountable
R=Responsible
C=Consulted
I=Informed

## RAM
|  | Templete Developed By - ISOBEX |  | www.isobex.com
Responsibility Assignment Matrix
Project Name | Construction of Cotton Mill | Location | Pune, India | Version No. | 1
Project Manager | John Smith | Client Name | Cotton Co-operative Society | Updated On | 2020-05-09
Start date | 2020-01-01 | End date | 2020-07-01
Activities | Rahesh | John | Elizabeth | Mathew | Reena
Design | P |  | S
Quality Check |  |  | P | S
Development |  | S |  |  | P
Resource Planning | S | P
Logistics | P |  |  | P | S
Procurement | P | S
Governance |  |  | P | S
| P= primary | s=Scondary

## OBS
|  | Templete Developed By - ISOBEX |  | www.isobex.com
Project Organization Breakdown Structure
Project Name | Construction of Cotton Mill | Location | Pune, India | Version No. | 1
Project Manager | John Smith | Client Name | Cotton Co-operative Society | Updated On | 2020-05-09
Start date | 2020-01-01 | End date | 2020-07-01
Deprtment 1 | Deprtment 2 | Deprtment 3 | Deprtment 4 | Deprtment n | Vendor 1 | Vendor 2 | Vendor 3 | Vendor 4 | Vendor 5
WBS No. 1.1.1 | WBS No. 1.2.1 | WBS No. 1.1.1 | WBS No. | WBS No. | WBS No. | WBS No. | WBS No. | WBS No. | WBS No.
WBS No. 1.1.2 | WBS No. 1.1.2 | WBS No. 1.3.3 | WBS No. | WBS No. | WBS No. | WBS No. | WBS No. | WBS No. | WBS No.
WBS No. 1.1.3 | WBS No. 1.2.3 | WBS No. 1.2.5 | WBS No. | WBS No. | WBS No. | WBS No. | WBS No. | WBS No. | WBS No.
WBS No. 1.1.4 | WBS No. 1.2.4 | WBS No. 1.3.5 | WBS No. | WBS No. | WBS No. | WBS No. | WBS No. | WBS No. | WBS No.
WBS No. 1.1.5 | WBS No. 1.2.5 | WBS No. 1.3.6 | WBS No. | WBS No. | WBS No. | WBS No. | WBS No. | WBS No. | WBS No.
WBS No. 1.1.6 | WBS No. 1.2.6 | WBS No. 1.3.7 | WBS No. | WBS No. | WBS No. | WBS No. | WBS No. | WBS No. | WBS No.

## Kick-off checklist
|  | Template Developed By - ISOBEX |  | www.isobex.com
Project Name |  | Customer Name
Project Department |  | Customer Location
Date of meeting
Project kick-off meeting checklist
S.No | Check Point | Tick if discussed | Notes
1 | Project location | Tick symbol | Pune, Mumbai
2 | Project sponsor (company or individual) | Tick symbol
3 | Key customer contacts |  | Finance -
4 | Project objectives
5 | Project scope and definition of change
6 | Success criteria
7 | Exit criteria
8 | Expected start date
9 | Expected end date
10 | Project manager
11 | Government rules, regulation, specific culture etc
12 | Deliverable sign-off authority
13 | Requirement sign-off authority
14 | Key stakeholders & their responsibility
15 | Organization chart
16 | Escalation matrix
17 | Material supplied by customer
18 | Assumptions
19 | Initial Risks
20 | Any risk to be handled immediately
21 | Any assumption to be validated immediately
22 | High level estimated efforts and duration
23 | Primary skills required.
24 | Any quality related expectation
25 | Any onsite/onshore/offsite/offshore travel require
26 | Travel expanses would be invoiced at actual
27 | Material or licenses procured would be invoiced at actual
28 | import export duty would be invoiced at actual
29 | Billable hours and known holidays
30 | Invoice to (name & address)
31 | Invoice frequency
32 | Invoiced on or before date
33 | Invoice clear on or before date
34 | Status reporting frequency
35 | Status call frequency
36 | Status report mailing list (To & Cc)
37 | Status report format
38 | Any specific metrics to be tracked in status report
39 | Status call attendee list
40 | Status call preferred time zone & time slot
** Purpose to confirm the information written in project charter and discuss those in details. Get any more information required for project execution.

## Schedule
Project Schedule
Project Name |  | Location |  | Version No.
Project Manager |  | Client Name |  | Updated On
Start date |  | End date
S.No | WBS No | Activity | Planned Efforts (hrs) | Actual Efforts | Planned Start date | Planned finish date | Actual Start date | Actual Finish Date | Effort Variance (Planned - Axtual) | Effort Variance (Planned Finished date- Axtual finish date)

## Retrospective
|  | Template Developed By - ISOBEX |  | www.isobex.com
Project Name | Construction of Cotton Mill | Location | Pune, India
Project Manager | John Smith | Client Name | Cotton Co-operative Society
Start date | 2020-01-01 | End date | 2020-07-01
Project Phase | End of Project | Retrospective Date | 2020-05-09
| What went well | What went wrong | What we will do better next time | Comments
Mathew | like cordination between various department and vendors were excellent. | Delay in procurement process caused risk of schedule slipage. | Schedule should be agreed with all department and vendors before commiting timelines | Everyone performed very well and delivered project on time. My suggestion is to include project manager or senior members to involve in vendor selection process.
Julie
Rajesh
Elizabeth
TechPpro Solutions Inc
Info Technologies
Stakeholder 3
Stakeholder n